## RahNdir Backlog
# adam zawej app Backlog
Goal : | Build java app for windows RahNdir a list todo in algerian manner
Delay : | 20 h = 20 work days |  | velocity = 01h/day
| begin : 26/09/2017 | end : 25/10/2017
Items (User Stories) :
|  | Priority | Estim/h
US 1 | UI App design | 2 | 2
US 2 | Masque de saisie (une fenetre) | 1 | 2
US 3 | imprimer exacte sur modele scané | 1 | 8
US 4 | Data Base (save my files, modif, delete) | 2 | 4
US 5 | quick Search engine | 2 | 2
US 6 | Advanced Search engine | 3 | 4
US 7 | Admin Page & login | 3 | 4
US 8 | Nice UI | 3 | 4
|  | Total = | 30 | h

## Sprint # 1
Sprint Backlog # 1
Goal : | Build the masque saisie window and the print engine
Delay : | 11 h = 05 work days |  | velocity = 02h/day
| begin : 14/03/2017 | end : 20/03/2017 |  |  | TODO | In Progress | Done
Items (User Stories) : |  |  |  |  | us3-Print engine | US2-Masque de saisie | US1-App Design
|  | Priority | Estim/h |  | us3-1
US 1 | App design | 2 | 1 |  | us3-2
US 2 | Masque de saisie (une fenetre) | 1 | 2 |  | us3-3
US 3 | imprimer exacte sur modele scané | 1 | 8
|  | Total = | 11 | h